## Slide 1: Mid-Year Programme Performance Review: Emerging Issues, Trends and Assessments Said Adejumobi, Director Strategic Planning, Oversight and Results Division (SPORD)
Q2 APPRM meeting
20th , 21st and 23rd July 2020
Addis Ababa, Ethiopia

## Slide 2
Objective of Q2 APPR meeting
Challenges and opportunities for programme delivery in the context of COVID-19
Trends and issues emerging from mid-term reports
OIOS Audit Recommendations: Implementation status
Key Recommendations of UN BoA Audits FY 2019
Conclusions
Outline of the Presentation

## Slide 3
Objective:
  enhance result-based planning, monitoring and reporting
  foster the culture of accountability and transparency.
Specific objectives
  take stock of progress made in implementing deliverables during Jan to June and review overall programme performance; and agree on remedial/ course correction measures (if any);
  review utilization of resources from all funding streams (RB, NEPAD, DA and XB);
  provide space for identifying concrete areas of cross-sectoral and cross-divisional collaboration; and
  deliberate on the strategic and programmatic implications of COVID-19
1. Objectives of the Quarter 2 APPR Meeting

## Slide 4
2. Challenges and opportunities for programme delivery in the context o f COVID 19
Challenges
Slow down in implementation due to travel restrictions (in some case no progress) compounded by recruitment freeze and phased release of RPTC resources
2. Impact on convening and operational functions
=> Likelihood of not meeting some performance targets
4. Undertaking evaluations during ‘lockdown’ => methodological shift
5. Slower resource usage - RB and XB - (Travels; Expert Meetings) repurposing / extending agreements for XBs
6. Rolling back the gains of the SDGs and decelerating the “Decade of Action”

## Slide 5
Opportunities
New business model that deploys technology and ICT for operational delivery
Financial prudency and cost efficiency through better use of technology
New development paradigm in a COVID 19/ post COVID context / ‘building back better’ / green recovery
4. Space for cross-sectoral collaboration and partnership within ECA, the UN and other stakeholders (knowledge resources, e.g. KM Hub on COVID-19
5. Push for innovation and creativity in the private sector in business operations
6. Strengthening governance systems in the service of people / health care systems through increased investment in infrastructure
… continued
2. Challenges and opportunities for programme delivery in the context o f COVID 19

## Slide 6
A. Some highlights of progress toward results / emerging results
3. Trends and issues emerging from mid-term reports
Policy direction and uptake for Africa on its response to COVID-19, including policy studies and briefs on the socio-economic impacts of COVID 19 at regional and sub-regional levels, “Exit Lockdown Strategies” and “COVID-19 and cities”; and coordinated regional and global action in support of the continent
The Africa Communication and Information Platform (ACIP) for Health & Economic Action
Incorporating post COVID 19 recovery plans in AfCFTA national strategies (Sierra Leone, Kenya and Gambia)
Strengthened systems of Civil Registration and Vital Statistics (Ethiopia, Senegal, Somalia, South Sudan, Sudan & Burkina Faso) as essential services and enhancing the role of statistics during the COV-19 Pandemic

## Slide 7
A. Some highlights of progress toward results / emerging results
3. Trends and issues emerging from mid-term reports
Launch of the 2019 Africa Regional Integration Index
Leveraging digital technologies through the Pharma Initiative to create access to safe, affordable medicine
Effective use of digital learning platforms for capacity development trainings with added advantage of reducing costs and increased women participation
Work with Afreximbank to support liquidity relief to the recovery of five African airlines from COVID-19 and in support of a bankable deal for Guinea to support imports and purchase of agricultural inputs to mitigate the impacts of COVID-19 on food security
Mali endorsed a Public Budgeting Framework sensitive to Demographic Dividend that will inform the country’s 2021 national budget deliberations
… continued

## Slide 8
  B. Status against performance targets as per the 2020 ABP (by SP)
… continued
3. Trends and issues emerging from mid-term reports
SPs | Indicators of Achievement |  |  |  |  |  |  |  | 
 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
SP1: MGD |  |  |  |  |  |  |  |  | 
SP2: RITD |  |  |  |  |  |  |  |  | 
SP3: PSFD |  |  |  |  |  |  |  |  | 
SP4: ACS |  |  |  |  |  |  |  |  | 
SP5: TCND |  |  |  |  |  |  |  |  | 
SP6: ACG |  |  |  |  |  |  |  |  | 
SP7: SRO-NA |  |  |  |  |  |  |  |  | 
NEPAD
Key:
 | >= 50% |  | < 50% & >=30% |  | < 30% |  | Data not provided / available |  | Data available by year end |  | Not applicable

## Slide 9
… continued
3. Trends and issues emerging from mid-term reports
SPs | Indicators of Achievement |  |  |  | 
 | 1 | 2 | 3 | 4 | 5
SP7: SRO-WA |  |  |  |  | 
SP7: SRO-CA |  |  |  |  | 
SP7: SRO-SA |  |  |  |  | 
SP7: SRO-EA |  |  |  |  | 
SP8: IDEP |  |  |  |  | 
SP9: PISP |  |  |  |  | 
  B. Status against performance targets as per the 2020 ABP (by SP)
Key:
 | >= 50% |  | < 50% & >=30% |  | < 30% |  | Data not provided / available |  | Data available by year end |  | Not applicable

## Slide 10
  B. Status against performance targets as per the 2020 ABP (by SP)
… continued
3. Trends and issues emerging from mid-term reports
Key observations/Challenges
Paucity of performance data
  Stepwise/ progressive nature of indicators: work starts in Q1 and results begin to emerge in Q3/Q4
  Back-loading of deliverables to Q3/Q4 due to travel ban, political instability (WA & NA) and late receipt of RPTC funds constrained data collection efforts/ monitoring visits
  Some performance data, e.g. volume of intra-Africa trade, only available by end of Q3 or 2020
  As at end of Q2, data only available for 56.8% of performance indicators (i.e. 29 out of 51)
50% or more of set targets achieved  for 13 out of the 29 indicators for which data is available
SPORD assessment incomplete due to unavailability of data
Likelihood of more red flags 
Focused attention required to review and speed up SPs’ work corresponding to performance indicators flagged  and .

## Slide 11
  Collaboration & joint delivery in Countries of Focus by thematic area
… continued
3. Trends and issues emerging from mid-term reports
National AfCFTA strategies
  RITD and SROs targeting all CoFs
  RITD, ACS and ACG targeting Kenya, Burkina Faso and Rwanda (Gender responsive trade policies)
  PSDFD, RITD, ACS and GPSPD on the impact of COVID-19 on African Ports targeting countries with ports
  IDEP and RITD on webinars/ Digital Trainings on AfCFTA and e-Commerce targeting all CoFs
2) Macro modelling for sustainable development planning
MGD and SRO-WA targeting ECOWAS
MGD, PCKMD & ACS targeting all CoFs (IPRT)
IDEP and MGD on training on Fiscal policy for Sustainable development targeting all COFs
IDEP and MGD – Webinars/ Digital Trainings on domestic resources mobilization and macroeconomic planning targeting all CoFs

## Slide 12
  Collaboration & joint delivery in Countries of Focus by thematic area
… continued
3. Trends and issues emerging from mid-term reports
3) Policy response to COVID-19 and advocacy
MGD, SRO-WA, ACS and TCND (Strategy for Governance of COVID-19 Stimulus Funds) targeting Guinea
MGD, SRO-SA and RITD on socioeconomic impacts of COVID-19 and customization of macroeconomic model targeting Namibia
4) Innovative financing
PSDFD & TCND on the implementation of the SDG 7 Initiative targeting Angola, Ethiopia, Guinea, Kenya, Senegal, and South Africa
PSDFD, MGD and SRO SA on domestic and private resource mobilization targeting Angola
5) Social policy for poverty and inequality reduction
PSDFD, RITD, GPSPD and ACS on the review land laws from a gender lens targeting Malawi
GSPD, ACS, SRO-WA, and SRO-SA on technical assistance to achieve migration-related targets of SDGs and the Global Compact targeting all CoFs

## Slide 13
Year 2018 to date, five audits were undertaken by OIOS; 28 recommendations made
  Africa Hall (2018, 2019 & 2020) (x3)
  ECA Policy Centers (x1)
  Streamlining SDGs in ECA Programme of Work (x1)
Since 2018 to date, ECA has implemented 13 recommendations. Key ones are:
  Risk management of Africa Hall project
  Improved programme management accountability framework
  Corporate level Enterprise Risk Management Framework (ERMF)
  Developed advocacy and outreach plan on VNRs
Two (2) recommendations not implemented by deadline & still pending:
  Developing a Resource Mobilization (RM) strategy for Africa Hall
  Strengthening capacity of Partnership Resource Mobilization Section (PRMS) by filling vacant posts for the section
13 audit recommendations with deadlines in 2020 in progress/on track
Africa Hall 2020 (x8) & Management of Policy Centres (x5)
4. OIOS Audit Recommendations: Implementation Status

## Slide 14
5. Key Recommendations of UN BoA Audits FY 2019
Recommendation | ECA comments
Strengthen oversight of extra budgetary resources, address low utilization. Actual utilization was only 58.58% in 2018 and 60.64% in 2019. | ECA takes good note of the recommendation, will take steps to further strengthen the review mechanisms, both in terms on delivery of outputs and financial burn rate. Deadline: ongoing
Carry out review, reasons for non-achievement of targets. Target indicators for 5 out of 9 sub-programmes for the biennium 2018-2019 were not met - RITD, PSDF, ACS, TCND, SRO (NA, WA & EA). | To further strengthen the planning and implementation of programme/projects ECA is currently revising its Programme Management Manual (PPM) to bring it at par with industry best practices. Deadline: ongoing

## Slide 15
Recommendation | ECA comments
Work closely with MSs to improve data collection for the SDGs. ECA has compiled indicator-wise data of 54 African countries for 17 goals for 2015 to 2019. No data was collected for any country for 80 indicators, while coverage of countries for many indicators was low. | Deadline: ongoing
Review reasons for delays in recruitment. ECA in 2019 took 340 days against benchmark of 120 day in completion of the entire recruitment process them | HR regularly follows up with all stakeholders of the recruitment process including the Hiring Managers as well as CRC/B/CRP members.HR also adopted a follow-up mechanism of informing the Executive Secretary cases on a weekly basis pending for selection on both paper and in INSPIRA.
… continued
5. Key Recommendations of UN BoA Audits FY 2019

## Slide 16
… continued
Recommendation | ECA comments
Improve management of Implementing Partners (IPs) – timely disbursement, benefits delivered & refunds timely received. As of 31 Dec 2019, 20 Implementing Partners (IPs) were to refund 68.6% of total amount disbursed | The balance amount will be collected or refunded or adjusted based on the agreement as per the advice of the concerned project managers who are overseeing the projects from the respective Divisions. Deadline Dec 2020
ECA takes steps to enhance involvement of Senior Leadership Team for planning and implementing ERM to ensure that ERM is embedded into strategic planning and decision-making. | A devoted capacity for risk management is currently being recruited. Deadline: Dec 2020
5. Key Recommendations of UN BoA Audits FY 2019

## Slide 17
Building back better in Africa: ECA strategy for integrated response to COVID-19
Strengthen collection of performance data, including evidence
Need to ensure systematic and timely implementation of audit and evaluation recommendations
Need to step-up and institutionalize ECA’s participation in the work of OIBCs with a Whole-of-System Approach
Need to operationalize the Decade of Action to deliver the SDGs
Engaging and collaborating with RCs/ UNCTs: need for engagement strategy
Increased use of technologies for collaboration, policy advice, dissemination of knowledge products, training and engagement with constituencies – Alternative and cost-efficient implementation modality to scale up reach and programe impact?
6. Conclusions

## Slide 18
Thank you !