## Slide 1: Sub-programme 7 Component 4: Sub-regional activities in Eastern Africa Andrew Mold Chief, Regional Integration and AfCFTA Cluster
2020 Second Quarter Accountability and Programme Performance Review Meeting
20 – 23 July 2020
[Virtual]

## Slide 2
2020 Progress on achievements (all budget sources: 18, 23, 11, 35)
Objective: To deepen regional integration in Eastern Africa by fostering the implementation of the African Continental Free Trade Area and harnessing the potential of the blue economy and tourism.
Progress made to achieving the result area
Result Area 1: Implementing the African Continental Free Trade Area: from vision to action in Eastern Africa
Indicator of Achievement | Baseline | 2020 Target | Actual (Qtr 2) | Progress
Increase in countries ratifying AfCFTA | 5 | 2 | - | Launch of AfCFTA Regional Report in Nairobi UNCT Reports on trade impacts of COVID-19 crisis on Rwanda and Uganda Consultations with Private Sector Federations and CoC
Increase in countries with AfCFTA strategies | 1 | 1 | 1 | Rwanda & Burundi AfCFTA strategies under-development Request from DRC and Comoros Work with ATPC to develop an EAC regional AfCFTA Strategy
Increase in the share of intraregional exports | 13.2% (2018) | 14.2% | Data not available | Analysis of trends post crisis in intra-regional trade with TMEA

## Slide 3
HOW? Delivery modalities – RA1
Target countries
  Burundi, Comoros, DRC, Kenya, Rwanda, Uganda, Seychelles
  RECs -
  EAC
  IGAD
  ICGLR
Alignment with ECA’s strategic directions
Joint delivery in Countries of Focus
AfCFTA implementation strategies for EAC, Burundi, & Rwanda – with ATPC & ECA Digital Centre for Excellence
ERA peer review with Private Sector Development and Finance Division.
Youth and COVID-19 forum with SRO-WA
Contributions to UNCTAD World Investment Report 2020
RITD – alignment of outputs
Response to COVID-19
  Sub-regional report on the impact of COVID-19 to Eastern Africa
  Economic impact assessments for COVID-19 on the economies of Djibouti, Uganda, Rwanda, Seychelles, EAC, ICGLR and IGAD
  COVID-19 dissemination; CNBC, KNICC webinar, Digital Forum 2020 La Tribune Afrique, blogs and Policy Brief for Brookings Institute and OECD, television debate on East African budgets (RTV), IDDRI on financing way out of crisis, etc.
Notes: IGAD- Djibouti, Eritrea, Ethiopia, Kenya, Somalia, Sudan, South-Sudan and Uganda
Great-Lakes Region- - Democratic Republic of the Congo (D.R.C.), Burundi, Rwanda, Republic of the Congo, and Uganda

## Slide 4
HOW? Delivery modalities - RA1
Gender Mainstreaming
  COVID-19 report has a section on gender implications & policy impacts on women, and youth
Contribution to the SDGs
  8.1.1, SDG 9.2 and SDG 17.4
Follow-up on ARFSD res.
  UN Decade of Action & UNDS to implement the 2030 and 2063 agendas- working with RECS (EAC) & UNCTs in Rwanda and Uganda to integrate sub-regional priorities in planning
OIBCs (if applicable)
  AfCFTA implementation contributed to O/IBC 2
Partnerships (external)
  Co-convened with RITD the East African Trade and Business webinar and Kenya National Chamber of Commerce and Industry (KNCCI)
  Policy Brief on Regional Trade with TMEA
  UNCT meetings in Djibouti, Eritrea, Rwanda and Uganda.
  Private Sector Federation Rwanda – convening private sector consultations on AfCFTA
Notes: EA Trade & Business webinar theme: COVID-19 Recovery Mechanisms and the AfCFTA