## Slide 1: URBANIZATION AND DEVELOPMENT SECTION Edlam Yemeru Chief, Urbanization and Development Section Gender, Poverty and Social Policy Division
2020 Second Quarter Accountability and Programme Performance Review Meeting
8-10 July 2020

## Slide 2
2020 Progress on achievements (all budget sources: 18, 23, 11, 35)
Objective: The objective, to which this subprogramme contributes, is to reduce poverty and inequality and advance inclusive social and spatial development in Africa.
Progress made to achieving the result area
Indicator of Achievement: Improved knowledge and capacity of African policy makers to design, implement and monitor urban policies and strategies Performance measures Baseline (2019) – 9 national and local governments Target (2020) – 6 national and local governments Actual (2020) – 2 national and 2 local governments
Result Area 1: Enhanced capacity of member States to design, implement and monitor urbanization policies, programmes and strategies in support of national development planning

## Slide 3
2020 Progress on achievements (all budget sources: 18, 23, 11, 35)
Progress made to achieving the result area
Operational 1. Strengthened knowledge and skills of African policy makers on integrating urbanization into national development, regional trade and industrialization plans and policies Regional (IDEP webinar on cities and regional integration; 8 wk training course on urbanization and economic growth) National- Ethiopia (National Regional Development Framework of Planning and Development Commission for the country’s 10 year prospective plan) National- Chad (Industrialization and Economic Diversification Plan) 2. Strengthened coherence and linkages between national and local voluntary reviews of Agendas 2030 and 2063 (dialogue and decisions at the 6th ARFSD; support for VLRs in Accra, Yaoundé, Harare, Victoria Falls, Ngora District, Addis Ababa; DESA global consultations on VLRs)

## Slide 4
2020 Progress on achievements (all budget sources: 18, 23, 11, 35)
Progress made to achieving the result area
Convening Advancing urban policy dialogue and prioritization with the African Union (AU Ministerial meeting on housing and urban development with AU STC No.8 in Feb 2020 at World Urban Forum; Africa-France Summit preparations; Regional review of the New Urban Agenda) Advancing Africa’s urban priorities through global advocacy and dialogue (policy dialogues and training at the World Urban Forum, Feb 2020) Think-tank Urban Economic Geography and Regional Trade in Africa (Regional report) The Role of Cities in Domestic Resource Mobilization (Regional Report) Guidelines for Voluntary Local Review in Africa (Policy guideline) Urbanization, growth and transformation: Uganda, Ethiopia, Chad (Case Studies) Accelerating Africa’s Industrialization: Why Cities Matter (Policy Brief) An Urban Lens in National Development Planning in Africa (Policy Brief)

## Slide 5
HOW? Delivery modalities – RA3
Target countries + Cities
  Countries: Chad, Ethiopia
  Cities: Accra (Ghana), Yaoundé (Cameroon), Ngora (Uganda), Victoria Falls (Zimbabwe)
Alignment with ECA’s strategic directions
  (pick the relevant ECA SD icon)
Joint delivery in Countries of Focus
  Chad: SRO/ CA
  Ethiopia: SRO-EA
  Ghana (Accra), Yaoundé (Cameroon) and Zimbabwe (Harare and Victoria Falls- TCND & ACS
  Conservation (TCND)
  Divisional (e.g. Youth policy; Human Security Index)
Response to COVID-19
Declaration and action plan of the AU STC No.8 on COVID-19 and Public Service, Local Government, Urban Development and Decentralization
Report on COVID-19 in African Cities (with UN-Habitat, UNCDF, UCLG-Africa, Shelter Afrique)
DA 13 project on Urban Economic Resilience to COVID-19 (DA 13 project)
SG’s policy brief on “Cities and COVID-19”

## Slide 6
HOW? Delivery modalities – RA3
Gender Mainstreaming
  Design
  Project implementation
  Capacity development
Contribution to the SDGs
  Targets 11.1;11.1a
  Target 1.1
  Targets 8.1, 8.2 and 8.3
Follow-up on ARFSD res.
  VLRs
  Regional guide on VLRs
  Support to additional local governments to conduct VLRs
OIBCs (if applicable)
  Leveraging new technologies and enabling digital transitions
Partnerships (external)
  AU (Political Affairs) on the New Urban Agenda, Africa-France Summit, COVID-19, VLRs
  UN Habitat on the New Urban Agenda, Africa-France Summit, COVID-19, VLRs
  UNCDF on COVID-19
  Regional Commissions on the New Urban Agenda, COVID-19
  UCLG-Africa on COVID-19
  Brookings Institution on urbanization and economic growth

## Slide 7
Key challenges
Lessons learnt
Status update: Key challenges and lessons learnt – RA3
COVID-19 related impacts present implementation constraints and new demands.
  Postponement of technical assistance activities especially in country consultations and events
  Slower data, responses and information from countries and partners
  Shifting member State priorities
Capacities for sustained technical support over time constrained beyond the end of projects.
Integrating COVID-19 into ongoing & planned work.
The relevance and value of virtual engagement as a mode of delivery for operations
A focus on same countries & cities for different deliverables, improves outreach and impact
The power of partnerships to deliver under resource constraints.

## Slide 8
THANK YOU!