## Slide 1
Risenga Maluleke
South Africa
2020 Round of Population and Housing Censuses
13th Africa Symposium on Statistical Development, Addis Ababa , Ethiopia

## Slide 2
The UN Conference on Population and Housing censuses was held in 2015 in New York
A resolution was taken on the 2020 World Population and Housing censuses. It recommends that all member states conducts at least one population and housing census during the 2020 round of censuses
The 2020 round of censuses should take into account:
  International and regional recommendations relating to population and housing censuses and giving particular attention to advance planning,
  Cost efficiency,
  Coverage and the timely dissemination of, and easy access to, census results in order to inform decisions and facilitate the effective implementation of development plans and programmes.
UN Conference – New York, 2015

## Slide 3
The UN resolution coincides with the South African plan to conduct the Census in 2021
The purpose of conducting the 2020 round of population and housing censuses is to ensure the coordination of activities amongst the member states
Statistics Act No. 6 of 1999 requires Statistics South Africa to conduct the population and housing census every 5 years – Reason for Census 2021
UN Conference – New York, 2015

## Slide 4
Enumerators repeat interviews if errors were detected by auto reject script
Interviewers synchronize their devices and upload completed questionnaires to Headquarters
Supervisors monitors and report on the Progress of the Fieldworkers
Questionnaires with all minimum required fields completed are automatically accepted by the headquarters
Content areas design questionnaires using visual tools and upload them to the central server (HQ)
Interviewers visit households and collect data
HQ distributes the sample lists across teams of enumerators
Data Flow for CS2016 and KZN CSS
A script is executed on completed data at headquarters to autoreject questionnaires without minimum acceptable criteria. Once accepted, the status is updated to Approved By supervisor, thereby playing the role of the role of the supervisor with respect to quality of completed questionnaires

## Slide 5
Lessons Learnt on Surveys in preparations for Census 2021 during the 2020 round of censuses

## Slide 6
What was planned

## Slide 7
Census 2011 | CS 2016 and KZN CSS | SADHS 2015
PAPI- total count Conventional methodology (listing and enumeration) Self-enumeration was implemented in addition to the traditional data method (drop-off system) CSAS system for Recruitment Reporting Forward and reverse logistics | Creation of FW units Use of tech: Geo-referenced DF Unpacking method Navigation application loaded on the electronic devices Assignment planning at HO using the CAPI system | 4 questionnaires, loaded on PDAs/Tablets Ratio – 1 FWS per team (1 male, 1 female, 1 logistics officer, 1 biomarker,1 publicity officer) Assignment planning at HO level to FWS; then FWS to FW and back

## Slide 8
What Worked

## Slide 9
Census 2011 | CS 2016 and KZN CSS | SADHS 2015
Deployment of DCC Structure – ratio of FWS/FW Call centre – identify respondents who were not enumerated KYFC created awareness in the public KTS for payment of fieldstaff Field structure of FWC-FWS-FW | QN easy to administer QN was user-friendly with automated skip function. QN auto validations embedded to circumvent input errors by fieldworkers. MAR was successful in doing quality checks OOS - FWSs received reports and verified The enforcement letters were used to get access in gated communities and also assisted with the conversion of refusals | Sound plans were drawn with substantial inputs from geography. Substantial use was made of geospatial and other technologies

## Slide 10
What did not work

## Slide 11
Census 2011 | CS 2016 and KZN CSS | SADHS 2015
Duration of listing very short Not enough time to QA listing Some areas did not follow proper enumeration procedure during census night. QN A was not properly administered by FWs –more prevalent in employment section where skip instructions were not followed. Extended enumeration period due to non/late delivery of some materials | System not picking up errors of multiple FW using the same login details Searching of QN by way of scrawl down from the workload leads to FW using the wrong QN System lack of auto assignment of QN in case of multiple HHs Navigating to a segment FWU Online recruitment a challenge especially on target recruitment | PSU Sample - delayed receipt of the sample from Methodology and Standards to facilitate proper planning Continuously changing timelines led to frustrations and delays Lack of clear decisions from management on a number of aspects

## Slide 12
Census 2011 | CS 2016 | SADHS 2015
Some areas did not follow proper enumeration procedure during census night. QN A was not properly administered by FWs –more prevalent in employment section where skip instructions were not followed. Extended enumeration period due to non/late delivery of some materials Access was deliberately denied Transport during fieldwork was a challenge | System not picking up errors of multiple FW using the same login details Searching of QN by way of scrawl down from the workload leads to FW using the wrong QN System unduly rejecting completed QN for minimum accessibility rule – need thorough testing The ratio of 1FWS:19FWs Lack of OOS Verification Tool (OOS) verification on the FWS app necessitating the FWS to use the FW tablet | Need to overcome the uncertainties introduced by the technology approach. Lack of consulting of subject matter specialists in the Geography section in the early phases of project.

## Slide 13
Census 2021

## Slide 14
The Census 2021 project has adopted an ambitious approach, that of maximising on ICT innovations, on the back of an improved GIF hence “Digital 2021 Census”
This aligns to the recently initiated Digital Transformation concept paper
The recent technological breaches of security at reputable organisations are a constant reminders for us to ensure that confidentiality of personal information is guaranteed as stipulated in the Stats Act 6 of 1999
The United Nations Statistical Division (UNSD) has produced Guidelines on the use of electronic data collection technologies in population and housing censuses
BACKGROUND [1/3]

## Slide 15
The guidelines emphasise amongst other things the following:
A sound decision-making process
  for understanding the value of introducing a particular technology solution, evaluating its cost-effectiveness and viability on the basis of key institutional, operational and social factors, and making such a decision on the basis of the information gathered during this process
Geospatial information and systems
  to integrate the census mapping, enumeration and data analysis phases as well as for improving the efficiency and effectiveness of field work operations
Effective security for IT systems and electronic data
  to prevent inappropriate disclosure of sensitive information and disruptions in critical operations
BACKGROUND [2/3]

## Slide 16
To create a credible census plan, anchored by continuous testing of these plans
We need to create adequate confidence internally and externally before the Census 2021 Pilot, that most changes we are introducing can handle the expected volumes, while not compromising on the quality of the statistical output
Therefore collaborative effort at various levels of society is key and setting up of structures and their terms of reference
All these should be well clarified in planning documents; the strategy; operational plans; project templates; etc.
BACKGROUND [3/3]

## Slide 17
To update a GIF consisting of the Dwelling Frame, EA and Place Names datasets
To create datasets to support the HR Recruitment tool
To develop a Navigation application
To develop a GIF Update application
BACKGROUND [3/3]

## Slide 18
KEY MILESTONES
Activities | Timelines
Internal stakeholder workshop 1 | March 2018
New methodology test | September 2018
Internal stakeholder workshop 2 | October 2018
Provincial workshops | October 2018
User consultations | February 2019
Questionnaire and developments | March 2019
Completion of all plans | March 2019
Specifications for the Materials (Mini Test) | March 2019
Geography GIF updates | March 2019
Community mobilization and advocacy | March 2019
FINANCIAL YEAR 2018/2019

## Slide 19
Activities | Timelines
System requirements and specifications | May 2019
Procurement (Mini Test) | May 2019
System development | July 2019
Infrastructure assessment | July 2019
Recruitment and appointment | August 2019
Training | September 2019
Integrated test (Data collection) | October 2019
Payment | November 2019
Specifications for Materials (Pilot) | December 2019
Debriefing | March 2020
Community mobilization and advocacy | March 2020
Geography GIF updates | March 2020
FINANCIAL YEAR 2019/2020
Mini Test

## Slide 20
Activities | Timelines
Instruments and systems update (System Review) | May 2020
Procurement (Pilot) | July 2020
Recruitment and appointment | August 2020
Forward logistics | August 2020
Training | September 2020
Data collection | October 2020
Payment | November 2020
Reverse logistics | November 2020
Secondary editing and imputation | November 2021
Analysis | December 2020
Debriefing and closure report | December 2020
Final Specifications for Materials (Main) | December 2020
System review | March 2021
Geography GIF updates | March 2021
FINANCIAL YEAR 2020/2021
Pilot

## Slide 21
Activities | Timelines
Community mobilization and advocacy | Mar 2021
National workshop | August 2021
Training | September 2021
Recruitment and appointment | August 2021
Procurement | May 2021
Forward logistics | August 2021
Geography GIF updates | June 2021
Data collection | October 2021
Payment | November 2021
PES | November 2021
Secondary editing and imputation | December 2021
Secondary editing and imputation (PES) | December 2021
Analysis | December 2021
Debriefing | December 2021
Analysis and matching (PES) | January 2022
FINANCIAL YEAR 2021/2022
Main Census

## Slide 22
Activities | Timelines
Dissemination | June 2022
Closure report | September 2022
Community mobilization and advocacy | March 2023
FINANCIAL YEAR 2022/2023