## Slide 1: Mr. David Luke African Trade Policy Centre (ATPC) Regional Integration and Trade Division
2020 Second Quarter Accountability and Programme Performance Review Meeting
8 – 10 July 2020
[Virtual]

## Slide 2
2020 Progress on achievements (all budget sources: 18, 23, 11, 35)
Objective: to strengthen regional cooperation and integration among member States through increased trade flows, improved industrialization and increased investments.
Progress made to achieving the result area
IoA.1 Increase in the share of intra-African trade in Africa’s total trade Baseline (2019) – 16.7% Target (2020) - 17.6% Actual 2020 – to be updated at the end of the year IoA.2 Increased number of countries that have ratified the Agreement Establishing the AfCFTA Baseline (2019) – 29 Target (2020) – 39 Actual – 30 IoA.3 Increased number of countries that formulate national strategies for the implementation of the AfCFTA with ECA’s technical support Baseline (2019) – 6 Target (2020) - 12 Actual (as of June) – 9 (Kenya, Gambia, Sierra Leone) IoA.4 Number of countries implementing AfCFTA national strategies with ECA’s technical support Baseline (2019) - 0 Target (2020) - 6 Actual (as of June) - 0
RA 1: Ratification, domestication and implementation of the African Continental Free Trade Area.
Covid-19 refocused national priorities, target may be affected
Key national staff working remotely, focus on public health
1st July has been changed, new date under consideration

## Slide 3
2020 Progress on achievements (all budget sources: 18, 23, 11, 35)
Progress made to achieving the result area
ATPC produced various policy briefs and publications on COVID -19 focused on informal traders, supply chains, technology, manufacturing, exist strategies, insights on african businesses reactions and outlook; Increased understanding on key challenges encountered by Africa businesses, policy makers and other groups that have been adversely affected by the pandemic. Will assist countries and business in their COVID 19 responses. Preparation of a Policy brief on "Africa’s diversification and its trade policy transformation" for T20 in preparation for G20. G20 member States were informed of the importance for them to support Africa's diversification and transformation through the AfCFTA; As a results G20 members States may provide financial and technical support to Africa towards implementation of AfCFTA reforms.
RA 1: Ratification, domestication and implementation of the African Continental Free Trade Area.

## Slide 4
2020 Progress on achievements (all budget sources: 18, 23, 11, 35)
Progress made to achieving the result area
ATPC Published a study on "An empirical assessment of the African Continental Free Trade Area modalities on goods". Informed and influenced AfCFTA negotiations on the modalities on trade in goods as well as signing/ratification process; key findings also fed into national AfCFTA implementation strategies; Will help member States implement and take better advantage of the AfCFTA reforms ATPC prepared the draft methodology for the AfCFTA Country Business Index to be rolled out for the collection of primary trade data to create ABCI and inform ECA research. ATPC finalized methodology for the Harmonized data collection manual for (ICBT) in ECOWAS It will increase reliability and comparability of ICBT data collection amongst ECOWAS Members; It will support accurate and reliable tracking of regional trade policy, and improve evidence based macroeconomic and trade policy making.
RA 1: Ratification, domestication and implementation of the African Continental Free Trade Area.

## Slide 5
2020 Progress on achievements (all budget sources: 18, 23, 11, 35)
Progress made to achieving the result area
ATPC provided 2 Experts to ECCAS Secretariat-1 in trade in goods and 1 in trade in services Assisted ECCAS member States with negotiations/implementation of AfCFTA Agreement. ECCAS member States are ready to submit AfCFTA tariffs concession and schedules of services commitments to the AUC; ECCAS member States are in better position to implement and take advantage of the AfCFTA Agreement. Completed and official launched the Africa Regional Integration Index (ARII) 2019 edition. Member States and REC’s have access to objective information on their regional integration performance; increased knowledge and capacity to use the information contained in ARII 2019 for policy analysis and policy development; Improved regional integration performance of Member States within their sub region and within Africa.
RA 1: Ratification, domestication and implementation of the African Continental Free Trade Area.

## Slide 6
2020 Progress on achievements (all budget sources: 18, 23, 11, 35)
Progress made to achieving the result area
ATPC issued revised guidelines for developing AfCFTA national strategies aimed at providing guidelines for the development of national strategies for the implementation of the AfCFTA for the State Parties to the Agreement. ATPC Supported Kenya, The Gambia and Sierra Leone in preparing national AfCFTA Strategies. Strategies will complement a broader development framework, on trade and industrial policy environment of each State Party to the Agreement. Guide the implementation of the AfCFTA by countries. Organised a Webinar on East African Business and Trade: COVID -19 Recovery Mechanism and the AfCFTA Follow-up to the AfCFTA Forum for East African Chambers of Commerce. Expected to help the East African region deal with the effects of the COVID -19 pandemic and prepare for the world after.
RA 1: Ratification, domestication and implementation of the African Continental Free Trade Area.

## Slide 7
2020 Progress on achievements (all budget sources: 18, 23, 11, 35)
Progress made to achieving the result area
ATPC finalized its Gender Strategy facilitates the integration of gender considerations in ATPC technical work-streams and activities, chats a path to gender equality and the empowerment of women, resulting in gender inclusive intra-African/ international trade and development outcomes ATPC produced Modules for Training of Trainers for women’s organisations on the AfCFTA: intended to support organisations representing female traders in domestic policy processes to implement the AfCFTA Agreement. Will result in stronger knowledge and awareness of the AfCFTA Agreement to support organisations to advocate for a gender-sensitive approach to the implementation of provisions that directly affect women; ensuring that the strategies reflect priorities and interventions that enable women to exploit new opportunities created under the AfCFTA; Publication of the ATPC DAILY DIGEST A daily information on trade, business and regional integration news and updates;
RA 1: Ratification, domestication and implementation of the African Continental Free Trade Area.

## Slide 8
2020 Progress on achievements (all budget sources: 18, 23, 11, 35)
Objective: to strengthen regional cooperation and integration among member States through increased trade flows, improved industrialization and increased investments.
Progress made to achieving the result area
IoA.1 Cumulative number of member States, regional economic communities and pan African institutions using ECA proposed policies for programmes on market institutions covering 2nd Phase issues of the AfCFTA (investment, competition, intellectual property and/or e-commerce) Baseline (2019) – 29 Target (2020) – 44 Actual (as of June) –37 IoA.2 Increased number of member States and Pan African Institutions taking steps to use regional value chains into their trade policies in the context of the AfCFTA Baseline (2019) – 0 Target (2020) – 40 Actual (as of June) – 34
RA 2: Enhanced capacity of member States to develop, implement and monitor policies and programmes on regional value chains, competition and investment.
ATPC contributed to the work which is being led by MIS

## Slide 9
2020 Progress on achievements (all budget sources: 18, 23, 11, 35)
Objective: to strengthen regional cooperation and integration among member States through increased trade flows, improved industrialization and increased investments.
Progress made to achieving the result area
A.1Increased number of member States that integrate industrialization into their national development policies and planning frameworks in the context of the AfCFTA Baseline (2019) - 6 Target (2020)- 15 Actual (as of June) – 8 (Kenya, Gambia, Sierra Leone)
RA3. Enhanced capacity of member States to integrate industrialization into their national development policies and planning frameworks in the context of the AfCFTA

## Slide 10
2020 Progress on achievements (all budget sources: 18, 23, 11, 35)
Progress made to achieving the result area
ATPC issued revised guidelines for developing AfCFTA national strategies aimed at providing guidelines for the development of national strategies for the implementation of the AfCFTA for the State Parties to the Agreement. ATPC Supported Kenya, The Gambia and Sierra Leone in preparing national AfCFTA Strategies. Strategies will complement a broader development framework, on trade and industrial policy environment of each State Party to the Agreement. Guide the implementation of the AfCFTA by countries. Assessment of bilateral trade flows over time in LAPSSET Assess changes in trade flows in terms of volume, value, and nature over time between Kenya, Ethiopia, and South Sudan as a result of the implementation of LAPSSET, to inform a proposal on innovative management and financing of infrastructure projects in Africa as well as urban report.
RA3. Enhanced capacity of member States to integrate industrialization into their national development policies and planning frameworks in the context of the AfCFTA

## Slide 11
HOW? Delivery modalities – RA1
Target countries
  AfCFTA National Strategies
  Zambia, Zimbabwe, Cote d’Ivoire, Togo, Guinea, Cameroon, The Gambia, Senegal, Sierra Leone;
  Gabon, Congo Brazzaville Burkina Faso, Guinea Bissau, Malawi, Namibia, Niger, Tunisia, Algeria, Mozambique, Rwanda, Benin; Chad, Gambia, Sudan, Kenya, Mauritania, Senegal, Djibouti, Sao Tome, Cabo verde, Comoros;
Alignment with ECA’s strategic directions
  (pick the relevant ECA SD icon)
Joint delivery in Countries of Focus
  SROs
  AfCFTA National Strategies (All Countries of Focus (CFs))
  GPSPD
  Report on Urbanization (all CF’s)
  Report-AfCFTA and Poverty
  MPGD
  Economic modelling( all CF’s)
  ACS, GPSPD
  Supply and use tables (Chad, Zimbabwe)
  DA project on gender responsive trade policies
  IDEP
  Capacity Building- AfCFTA and Gender equality (all CF’s)
  PSDFD
  Trade facilitation ( All CF’s)
Response to COVID-19
  Preparation of Policy Briefs and publications:
    Focused on : informal traders, supply chains dimensions, applications technology, manufacturing and trade, insights on african businesses reactions and outlook.
  Organised a Webinar on East African Business and Trade:
    Recovery Mechanisms and the AfCFTA in East Africa.

## Slide 12
HOW? Delivery modalities - RA1
Gender Mainstreaming
  ATPC Prepared the initial Draft of its Gender Strategy.
  Modules for Training of trainers for women’s organisations on the AfCFTA.
Contribution to the SDGs
  (pick the relevant SDGs icon, as applies)
  3 AfCFTA Strategies will facilitate market access within the AfCFTA Market.
Follow-up on ARFSD res.
OIBCs (if applicable)
  Contributing to the work of O/IBC 2 on 2 of its pillars;
    AfCFTA
    COVID-19 Response
Partnerships (external)
  IFPRI online training course on the AfCFTA;
  ECCAS – ECA provided two trade experts that have helped region advance on AfCFTA negotiations;
  AUC - finalization of AfCFTA outstanding issues;
  Afreximbank partnerships on ICBT and IATF 2021 & 2023
  TRAPCA & tralac –ACP Project
  GAC & EU- AfCFTA Project
  UNCTAD –Services Project
  UNRC-AfCFTA National Strategies
  UNDA Project- gender-responsive trade policies

## Slide 13
Key challenges
Lessons learnt
Status update: Key challenges and lessons learnt – RA1
Continued uncertainty caused by COVID-19 on the operationalization of the AfCFTA;
COVID-19 has affected ATPC’s ability to support the AfCFTA negotiations and advocacy processes;
COVID-19 may affect the ability of some countries to implement the AfCFTA;
COVID-19 has resulted in reduced trade flows among member States.
Use virtual meetings to ensure that key meetings take place and the start of trade is not affected;
Ensure operational readiness in order to kick start processes when implementation resumes (Consultations with national counterparts, with SROs, finalization of ToRs and selection of experts etc.)
Maintain close contact with AUC political leadership to understand areas that require interventions for high impact.
Strengthen trade dimensions of post recovery plans in National Strategies.

## Slide 14
THANK YOU!